## US
node Management - N/A
Identity- Shuran |  | Part 1 / 2 / 3-5 | Notes | Story Points | Assignee | PR
US 1.1.1 | As an author, I want a consistent identity per node, so that URLs to me/my entries are predictable and don't stop working. Note: This includes API links and web frontend links. Note: This doesn't include authors/entries that are deleted. | Part 1 (Due Oct 20) |  |  | ✅
US 1.2.1 | As a node admin, I want to host multiple authors on my node, so I can have a friendly online community. | Part 1 (Due Oct 20) |  |  | ✅
US 1.3.1 | As an author, I want a public page with my profile information, so that I can link people to it. | Part 2 (Due Nov 3) | User profile link should be sharable, for example: https:ghostwhite...etc.../LinhNguyen310 -> show profile page |  | Evelyn Nguyen | https://github.com/uofa-cmput404/f25-project-ghostwhite/pull/12
US 1.4.1 | As an author, I want to my (new, public) GitHub activity to be automatically turned into public entries, so everyone can see my GitHub activity too. | Part 2 (Due Nov 3) |  |  | Michael
US 1.5.1 | As an author, I want my profile page to show my public entries (most recent first), so they can decide if they want to follow me. | Part 2 (Due Nov 3) |  |  | Evelyn Nguyen | https://github.com/uofa-cmput404/f25-project-ghostwhite/pull/12
US 1.6.1 | As an author, I want to be able to edit my profile: name, description, picture, and GitHub. | Part 1 (Due Oct 20) |  |  | ✅
US 1.7.1 | As an author, I want to be able to use my web browser to manage my profile, so I don't have to use a clunky API. | Part 1 (Due Oct 20) |  |  | ✅
Posting - Ximeng and Evelyn |  | Parts | Notes | Story Points | Assignee
US 2.1.1 | As an author, I want to make entries, so I can share my thoughts and pictures with other local authors. | Part 1 (Due Oct 20) | BE: Post API for creating | 1.5 | ✅
US 2.2.1 | As an author, I want my node to send my entries to my remote followers and friends, so that remote authors following me can see them. ⧟ Part 3-5 only | Part 3-5 Only (Later) |  |  | ✅ | ✅
US 2.3.1 | As an author, I want to edit my entries locally, so that I'm not stuck with a typo on a popular entry. -- That is, authors should not have to delete and re-create an entry to change the content. | Part 1 (Due Oct 20) | BE: PUT/PATCH API for updating | 1.5 | ✅
US 2.4.1 | As an author, I want my node to re-send entries I've edited to everywhere they were already sent, so that people don't keep seeing the old version. ⧟ Part 3-5 only | Part 3-5 Only (Later) | update and sync |  | ❌ | part4
US 2.5.1 | As an author, entries I make can be in CommonMark, so I can give my entries some basic formatting. | Part 1 (Due Oct 20) | bold, italic, etc. | 0.5 | ✅
US 2.6.1 | As an author, entries I make can be in simple plain text, because I don't always want all the formatting features of CommonMark. | Part 1 (Due Oct 20) |  |  | ✅
US 2.7.1 | As an author, entries I create can be images, so that I can share pictures and drawings. | Part 1 (Due Oct 20) | images | 1.5 | ✅
US 2.8.1 | As an author, entries I create that are in CommonMark can link to images, so that I can illustrate my entries. | Part 2 (Due Nov 3) | image links You want your publishing system (e.g., your writing platform or website) to support Markdown image syntax — so when you include that line, it correctly displays the image in your published post. ![Alt text](https://example.com/image.jpg) |  | Ximeng Duan | ✅
US 2.9.1 | As an author, I want to delete my own entries locally, so I can remove entries that are out of date or made by mistake. | Part 1 (Due Oct 20) | delete | 0.5 | ✅
US 2.10.1 | As an author, I want my node to re-send entries I've deleted to everyone they were already sent, so I know remote users don't keep seeing my deleted entries forever. ⧟ Part 3-5 only | Part 3-5 Only (Later) |  |  | ❌ | part4
US 2.11.1 | As an author, I want to be able to use my web-browser to manage/author my entries, so I don't have to use a clunky API. -- We don't want authors to have to use some interface like django-rest-framework or Swagger. | Part 1 (Due Oct 20) |  | 0.5 | ✅
US 2.12.1 | As an author, other authors cannot modify my entries, so that I don't get impersonated. | Part 1 (Due Oct 20) | related to 2.3.1 | 0 | ✅
Reading - Krystal |  | Parts | Notes | Story Points | Assignee
US 3.1.1 | As an author, I want a "stream" which shows all the entries I should know about, so I don't have to switch between different pages. | Part 1 (Due Oct 20) | main and for you pages | 1.5-2 | ✅
US 3.1.2 | ▪️As an author, I want my stream page to show me all the public entries my node knows about, so I can find new people to follow. | Part 1 (Due Oct 20) | all the public entries -> both follow/unfollow | 1.5 | ✅
US 3.1.3 | ▪️As an author, I want my stream page to show me all the unlisted and friends-only entries of all the authors I follow. | Part 2 (Due Nov 3) | unlisted and friends-only entries -> follow |  | Krystal Kim | ✅
US 3.1.4 | ▪️As an author, I want my stream page to show me the most recent version of an entry if it has been edited. | Part 1 (Due Oct 20) | handled in 2.3.1 | 0 | ✅
US 3.1.5 | ▪️As an author, I want my stream page to not show me entries that have been deleted. | Part 1 (Due Oct 20) | delete - related to 2.9.1 | 0 | ✅
US 3.2.1 | As an author, I want my "stream" page to be sorted with the most recent entries first. | Part 1 (Due Oct 20) |  | 0.5 | ✅
Visibility - Krystal |  | Parts | Notes | Story Points | Assignee
US 4.1.1 | As an author, I want to be able to make my entries "public", so that everyone can see them. | Part 1 (Due Oct 20) |  | 1 | ✅
US 4.2.1 | As an author, I want to be able to make my entries "unlisted," so that my followers see them, and anyone with the link can also see them. | Part 2 (Due Nov 3) | followers or link; need link |  | Krystal Kim | ✅
US 4.3.1 | As an author, I want to be able to make my entries "friends-only," so that I don't have to worry about people I don't know seeing them. | Part 2 (Due Nov 3) | follow-follow |  | Krystal Kim | ✅
US 4.4.1 | As an author, I want my friends to see my friends-only, unlisted, and public entries in their stream. | Part 2 (Due Nov 3) |  |  | Krystal Kim | ✅
US 4.5.1 | As an author, I want anyone following me to see my unlisted and public entries in their stream. | Part 2 (Due Nov 3) |  |  | Krystal Kim | ✅
US 4.6.1 | As an author, I want everyone to see my public entries in their stream. | Part 2 (Due Nov 3) | categorized public/unlisted/friends-only |  | Krystal Kim | ✅
US 4.7.1 | As an author, I want everyone to be able to see my public and unlisted entries, if they have a link to it. | Part 2 (Due Nov 3) | need link |  | Krystal Kim | ✅
US 4.8.1 | As an author, I don't anyone who isn't a friend to be able to see my friends-only entries and images, so I can feel safe about writing. | Part 2 (Due Nov 3) |  |  | Krystal Kim | ✅
US 4.9.1 | As an author, I don't want anyone except the node admin to see my deleted entries. | Part 1 (Due Oct 20) | django soft delete | 0.5-1 | ✅
US 4.10.1 | As an author, entries I create should always be visible to me until they are deleted, so I can find them to edit them or review them or get the link or whatever I want to do with them. | Part 1 (Due Oct 20) | django soft delete |  | ✅
Sharing |  | Parts | Notes | Story Points | Assignee
US 5.1.1 | As a reader, I can get a link to a public or unlisted entry, so I can send it to my friends over email, discord, slack, etc. | Part 2 (Due Nov 3) | get links |  | Ximeng Duan | ✅
US 5.2.1 | As a node admin, I want to push images to users on other nodes, so that they are visible by users of other nodes. ⧟ Part 3-5 only. | Part 3-5 Only (Later) |  |  | ❌ | ✅
US 5.3.1 | As an author, I should be able to browse the public entries of everyone, so that I can see what's going on beyond authors I follow. -- Note: this should include all local public entries and all public entries received in any inbox. | Part 2 (Due Nov 3) |  |  | Ximeng Duan | ✅
Following/Friends - Stan & Michael |  | Parts | Notes | Story Points | Assignee
US 6.1.1 | As an author, I want to follow local authors, so that I can see their entries. | Part 1 (Due Oct 20) |  |  | ✅
US 6.2.1 | As an author, I want to follow remote authors, so that I can see their entries. ⧟ Part 3-5 only. | Part 3-5 Only (Later) |  |  | ❌ | ✅
US 6.3.1 | As an author, I want to be able to approve or deny other authors following me, so that I don't get followed by people I don't like. | Part 1 (Due Oct 20) | approve/deny |  | ✅
US 6.4.1 | As an author, I want to know if I have "follow requests," so I can approve them. | Part 1 (Due Oct 20) | follow request |  | ✅
US 6.5.1 | As an author, I want to unfollow authors I am following, so that I don't have to see their entries anymore. | Part 2 (Due Nov 3) | unfollow |  | Stan Qiu | ✅
US 6.6.1 | As an author, if I am following another author, and they are following me (only after both follow requests are approved), I want us to be considered friends, so that they can see my friends-only entries. | Part 2 (Due Nov 3) | friends = following each other |  | Stan Qiu | ✅
US 6.7.1 | As an author, I want to unfriend other authors by unfollowing them, so that they can no longer see my friends-only entries. | Part 2 (Due Nov 3) |  |  | Stan Qiu | ✅
US 6.8.1 | As an author, my node will know about my followers, who I am following, and my friends, so that I don't have to keep track of it myself. | Part 2 (Due Nov 3) | ongoing... |  | Stan Qiu | ✅
Comments/Likes - Ximeng |  | Parts | Notes | Story Points | Assignee
US 7.1.1 | As an author, I want to comment on entries that I can access, so I can make a witty reply. | Part 1 (Due Oct 20) |  | 0.5 | ✅
US 7.2.1 | As an author, I want to like entries that I can access, so I can show my appreciation. | Part 1 (Due Oct 20) |  | 0.5 | ✅
US 7.3.1 | As an author, I want to like comments that I can access, so I can show my appreciation. | Part 1 (Due Oct 20) |  | 0.5 | ✅
US 7.4.1 | As an author, when someone sends me a public entry I want to see the likes, so I can tell if it's good or not. | Part 1 (Due Oct 20) |  |  | ✅
US 7.5.1 | As an author, comments on my friends-only entries are visible only to my friends and the comment's author. | Part 2 (Due Nov 3) |  |  | Ximeng Duan
US 7.6.1 | Update and delete comments by the comment's author | Part 2 (Due Nov 3) |  |  | Ximeng Duan | ✅
Node Management - N/A |  | Parts | Notes | Story Points | Assignee
US 8.1.1 | As a node admin, images can be hosted on my node, so that my users can use them in their CommonMark entries. | Part 2 (Due Nov 3) |  |  | Shuran Kong | ✅
US 8.2.1 | As a node admin, I want to be able to add, modify, and delete authors, to fix problems or remove unwanted users. | Part 2 (Due Nov 3) |  |  | Shuran Kong | ✅
US 8.3.1 | As a node admin, I want to be able to allow users to sign-up but require my approval to complete sign-up and use my node, so that I can prevent unwanted users and spambots. | Part 2 (Due Nov 3) |  |  | Shuran Kong | ✅
US 8.4.1 | As a node admin, I want to be able to connect to remote nodes by entering only the URL of the remote node, a username, and a password, so that I don't have to edit code. ⧟ Part 3-5 only. | Part 3-5 Only (Later) |  |  | ❌ | ✅ | when there are wrong username or password, we should get error
US 8.5.1 | As a node admin, I want a RESTful interface for most operations, so that I can connect to other nodes and allow my users to use alternate clients other than the web frontend. | Part 2 (Due Nov 3) | handled in part1 |  | Shuran Kong | ✅
US 8.6.1 | As a node admin, I want to be able to add nodes to share with. ⧟ Part 3-5 only. | Part 3-5 Only (Later) |  |  | ❌ | ✅
US 8.7.1 | As a node admin, I want to be able to remove nodes and stop sharing with them. ⧟ Part 3-5 only. | Part 3-5 Only (Later) |  |  | ❌ | Part 4
US 8.8.1 | As a node admin, I can prevent nodes from connecting to my node if they don't have a valid username and password. ⧟ Part 3-5 only. | Part 3-5 Only (Later) |  |  | ❌ | Part 4
US 8.9.1 | As a node admin, node to node connections can be authenticated with HTTP Basic Auth, so that I don't have to deal with tokens. ⧟ Part 3-5 only. | Part 3-5 Only (Later) |  |  | ❌ | ✅
US 8.10.1 | As a node admin, I can disable the node to node interfaces for connections that I no longer want, in case another node goes bad. ⧟ Part 3-5 only. | Part 3-5 Only (Later) |  |  | ❌ | Part 4
US 8.11.1 | As a node admin, I want everything to be stored in a well-indexed relational database, so that my website is snappy, and I can write SQL to fix things if I need to, make backups, etc... -- Use Postgres on Heroku and SQLite for testing on your local machine. -- Other DBaaS (e.g. Firebase) is forbidden. | Part 3-5 Only (Later) | ongoing... |  | Evelyn Nguyen | ✅
US 8.12.1 | As a node admin, I don't want arrays to be stored in database fields, so that my node won't get slower over time. | Part 1 (Due Oct 20) | 0 - included in database design |  |  | ✅
US 8.13.1 | As a node admin, I don't want to have seperate frontend and backend web servers, so I don't have to manage two web servers/services. | Part 1 (Due Oct 20) | https://docs.djangoproject.com/en/4.0/topics/templates/ | 1 |  | ✅
US 8.14.1 | As a node admin, I want deleted entries stay in the database and only be removed from the UI and API, so I can see what was deleted. | Part 1 (Due Oct 20) | Already handled in part 1 - Please test when you log in as admin |  |  | ✅
US 8.15.1 | As a node admin, I want my node's UI to only communicate with my nodes web server, so I can prevent XSS. | Part 2 (Due Nov 3) |  |  | Shuran Kong | ✅
US 8.16.1 | As a node admin, I want the API objects (authors, entries, etc.) to be identified by their full URL, to prevent collisions with other node's numbering schemes. ⧟ Part 3-5 only. | Part 3-5 Only (Later) |  |  | ❌ | ✅
US 8.16.2 | Design database schemas and relationships | Part 1 (Due Oct 20) |  | 5 | ✅ | ✅
Notifications (Inbox) |  | Parts | Notes | Story Points | Assignee
US 9.1.1 | Add notifications for like/ comment | Part 3-5 Only (Later) |  |  |  | ✅ | Check unit tests
Backlog |  | Parts | Notes | Story Points | Assignee
US 10.1.1 | Add fqid | Part 2 (Due Nov 3) | ex) "http://nodebbbb/authors/222/entries/293" |  | Evelyn Nguyen | ✅
US 10.1.2 | Add unit test to ensure at least 50% coverage | Part 2 (Due Nov 3) |  |  | everyone
US 10.1.3 | Deploy to heroku | Part 3-5 Only (Later) |  |  | everyone | ✅